## Trang tính1
DailyScrum - Meeting Minutes
Day 2 | Writer: Le Van Tuyen
|  | Total number of attendees: | 23/26
|  | Absent member: | Nguyen Duy Phuoc
Nguyen Duy Kiet
Nguyen Quang Tu
|  | Current progress of each member: | Name | Status | Notes
|  |  | Nguyen Duy Phuoc | None | None
|  |  | Nguyen Duy Kiet | None | None
|  |  | Nguyen Quang Tu | None | None
Summary of meeting content:
|  | Item | Deadline
|  | Team BA, Tester send file SQL | 22:00 04/10/2024
|  | Result of the framework selection discussion | 22:00 03/10/2024
Day 3 | Writer: Pham Dac Thinh
|  | Total number of attendees: | 19/26
|  | Absent member: | Le Xuan Luong
Cao Nguyen Vu
Ngo Tan Khoa
Nguyen Duy Kiet
Nguyen Quang Tu
Pham Ngoc Hung
Nguyen Phan Ngoc Tran
|  | Current progress of each member: | Name | Status | Notes
|  |  | Le Xuan Luong | None | None
|  |  | Cao Nguyen Vi | None | Have a schedule school
|  |  | Ngo Tan Khoa | None | None
|  |  | Nguyen Duy Kiet | None | None
|  |  | Nguyen Quang Tu | None | None
|  |  | Pham Ngoc Hung | None | None
|  |  | Nguyen Phan Ngoc Tran | None | None
Summary of meeting content:
|  | Item | Deadline
|  | DEV + TESTER + BA: Choose template for "Apartment management website in the USA" | 22:00 04/10/2024
DEV: Code form Login
TESTER: Research and write test cases according to the template
Day 4 | Nguyen Thuy Nga
|  | Total number of attendees: | 18/26
|  | Absent member: | Phan Dinh Yen
Le Dang Thong
Ngo Tan Khoa
Nguyen Bich Tram
Nguyen Duy Kiet
Nguyen Quang Tu
Pham Ngoc Hung
Nguyen Le Quoc Bao
|  | Current progress of each member: | Name | Status | Notes
|  |  | Phan Dinh Yen | None | None
|  |  | Le Dang Thong | None | None
|  |  | Ngo Tan Khoa | None | None
|  |  | Nguyen Bich Tram | None | None
|  |  | Nguyen Duy Kiet | None | None
|  |  | Nguyen Quang Tu | None | None
|  |  | Pham Ngoc Hung | None | None
|  |  | Nguyen Le Quoc Bao | None | Have a schedule school
Summary of meeting content:
|  | Item | Deadline
BA: Present the overall operations and outline the system's interface
DEV: Learn the process of using GITHUB
TESTER: Learn about error logging and error management process on GIT
Day 5 | Le Thi Thuy Tram
|  | Total number of attendees: | 19/26
|  | Absent member: | Pham Dac Thinh
Nguyen Duc Phuoc
Le Dang Thong
Duong Ngoc Danh
Nguyen Duy Kiet
Nguyen Quang Tu
Pham Ngoc Hung
|  | Current progress of each member: | Name | Status | Notes
|  |  | Pham Dac Thinh | None | Have a schedule school
|  |  | Nguyen Duc Phuoc | None | Have a schedule school
|  |  | Le Dang Thong | None | None
|  |  | Duong Ngoc Danh | None | None
|  |  | Nguyen Duy Kiet | None | None
|  |  | Nguyen Quang Tu | None | None
|  |  | Pham Ngoc Hung | None | None
Summary of meeting content:
|  | Item | Deadline
|  | BA: Take charge of assigning other members to design together and export FIGMA screens to image files | 12:00 08/10/2024
|  | DEV + TESTER: Design figma | 12:00 08/10/2024
Day 6 | Phan Dinh Yen
|  | Total number of attendees: | 23/26
|  | Absent member: | Do Thi Quynh My
Hoang Thi Thanh Tuyen
Pham Dac Thinh
|  | Current progress of each member: | Name | Status | Notes
|  |  | Do Thi Quynh My | None | Have a schedule school
|  |  | Hoang Thi Thanh Tuyen | None | Have a schedule school
|  |  | Pham Dac Thinh | None | Have a schedule school
Summary of meeting content:
|  | Item | Deadline
|  | BA + Tester: Revise FIGMA based on Mentor's comments. | 22:00 09/10/2024
|  | BA + Tester: Learn how to test Web Interfaces using Responsive techniques. | 22:00 09/10/2024
|  | DEV: Try any screen with responsive. | 22:00 09/10/2024
Day 7 | Nguyen Quang Hai
Total number of attendees:
Absent member:
Summary of meeting content:
|  | Item | Deadline
|  | Continue editing FIGMA. | 22:00 10/10/2024
|  | Meet and discuss together to design the relational database schema of the entire software. | 22:00 10/10/2024
Day 8 | Nguyen Duc Phuoc
|  | Total number of attendees: | 19/26
|  | Absent member: | Lê Đặng Thông
Nguyễn Bích Trâm
Nguyễn Duy Kiệt
Nguyễn Quang Tú
Pham Ngọc Hùng
Pham Dac Thinh
Nguyễn Phan Ngọc Trân
|  | Current progress of each member: | Name | Status | Notes
|  |  | Lê Đặng Thông | None | None
|  |  | Nguyễn Bích Trâm | None | None
|  |  | Nguyễn Duy Kiệt | None | None
|  |  | Nguyễn Quang Tú | None | None
|  |  | Pham Ngọc Hùng | None | None
|  |  | Pham Dac Thinh | None | None
|  |  | Nguyễn Phan Ngọc Trân | None | None
Summary of meeting content:
|  | Item | Deadline
|  | BA + Tester + Dev: Review and then submit the db schema. | 9:30 11/10/2024
|  | BA + Tester + Dev: With mentor, review db schema together. | 11:00 11/10/2024
|  | BA + Tester + Dev: Revise db schema based on Mentor's comments and create data for db | 22:00 11/10/2024
Day 9 | Le Xuan Luong
|  | Total number of attendees: | 13/26
|  | Absent member: | Phạm Đắc Thịnh
Nguyễn Thúy Nga
Lê Thị Thùy Trâm
Phan Đình Yên
Nguyễn Quang Hải
Ngô Tấn Khoa
Nguyễn Bích Trâm
Dương Ngọc Danh
Nguyễn Duy Kiệt
Nguyễn Quang Tú
PhamNgocHung
Lê Văn Tuyến
NguyenLeQuocBao
|  |  | Name | Status | Notes
|  |  | Phạm Đắc Thịnh | None | None
|  |  | Nguyễn Thúy Nga | None | None
|  |  | Lê Thị Thùy Trâm | None | None
|  |  | Phan Đình Yên | None | None
|  |  | Nguyễn Quang Hải | None | None
|  |  | Ngô Tấn Khoa | None | None
|  |  | Nguyễn Bích Trâm | None | None
|  |  | Dương Ngọc Danh | None | None
|  |  | Nguyễn Duy Kiệt | None | None
|  |  | Nguyễn Quang Tú | None | None
|  |  | PhamNgocHung | None | None
|  |  | Lê Văn Tuyến | None | None
|  |  | NguyenLeQuocBao | None | None
Summary of meeting content:
|  | Item | Deadline
|  | BA :Write all user stories for the entire system. | 22:00 14/10/2024
|  | DEV: Select one or a few screens to start coding. | 22:00 14/10/2024
|  | Tester :Divide the tasks among each other to write test cases for the entire system. | 22:00 14/10/2024
Day 10 | HoangThiThanhTuyen
Total number of attendees:
|  | Absent member: | Phạm Đắc Thịnh
Lê Đặng Thông
Nguyễn Bích Trâm
Dương Ngọc Danh
Nguyễn Duy Kiệt
Nguyễn Quang Tú
PhamNgocHung
|  | Current progress of each member: | Name | Status | Notes
|  |  | Phạm Đắc Thịnh | None | out the project
|  |  | Lê Đặng Thông | None | None
|  |  | Nguyễn Bích Trâm | None | out the project
|  |  | Dương Ngọc Danh | None | out the project
|  |  | Nguyễn Duy Kiệt | None | out the project
|  |  | Nguyễn Quang Tú | None | out the project
|  |  | PhamNgocHung | None | out the project
Summary of meeting content:
|  | Item | Deadline
|  | BA: Write and edit user stories for the entire system | 22:00 15/10/2024
|  | DEV: Continue to code functions (screen) | 22:00 15/10/2024
|  | Tester: Continue writing test cases for functions (screens) | 22:00 15/10/2024
Day 11 | Le Dang Thong
Total number of attendees:
Absent member:
Current progress of each member:
|  | Item | Deadline
Day 12 | Cao Nguyen Vu
|  | Total number of attendees: | 13/26
|  | Absent member: | Phạm Đắc Thịnh
Lê Xuân Lượng
Lê Đặng Thông
Ngô Tấn Khoa
Nguyễn Bích Trâm
Dương Ngọc Danh
Nguyễn Duy Kiệt
Nguyễn Quang Tú
PhamNgocHung
|  | Current progress of each member: | Name | Status | Notes
|  |  | Phạm Đắc Thịnh | None | out the project
|  |  | Lê Xuân Lượng | None | None
|  |  | Lê Đặng Thông | None | None
|  |  | Ngô Tấn Khoa | None | None
|  |  | Nguyễn Bích Trâm | None | out the project
|  |  | Dương Ngọc Danh | None | out the project
|  |  | Nguyễn Duy Kiệt | None | out the project
|  |  | Nguyễn Quang Tú | None | out the project
|  |  | PhamNgocHung | None | out the project
|  | Item | Deadline
|  | BA: Write and edit user stories, update document and screen for the entire system | 22:00 17/10/2024
|  | DEV: Update database, Continue to code functions (screen) | 22:00 17/10/2024
|  | Tester: Continue writing test cases for functions (screens) | 22:00 17/10/2024
Day 13 | Cai Hoang Long
|  | Total number of attendees: | 17/26
|  | Absent member: | Pham Dac Thinh
Le Xuan Luong
Le Dang Thong
Ngo Tan
Nguyen Bich Tram
Duong Ngoc Danh
Nguyen Duy Kiet
Nguyen Quang Tu
Pham Ngoc Hung
|  | Current progress of each member: | Name | Status | Notes
|  |  | Pham Dac Thinh | None | None
|  |  | Le Xuan Luong | None | None
|  |  | Le Dang Thong | None | None
|  |  | Ngo Tan | None | None
|  |  | Nguyen Bich Tram | None | None
|  |  | Duong Ngoc Danh | None | None
|  |  | Nguyen Duy Kiet | None | None
|  |  | Nguyen Quang Tu | None | None
|  |  | Pham Ngoc Hung | None | None
|  | Item | Deadline
|  | Change requirement | 22:00 18/10/2024
Day 14 | Ngo Tan Khoa
|  | Total number of attendees: | 14/26
|  | Absent member: | Pham Dac Thinh
Nguyen Thuy Nga
Nguyen Duc Phuoc
Le Thi Thuy Tram
Le Xuan Luong
Le Dang Thong
Nguyen Bich Tram
Duong Ngoc Danh
Nguyen Duy Kiet
Nguyen Quang Tu
Ly Phuc Tho
Pham Ngoc Hung
|  | Current progress of each member: | Name | Status | Notes
|  |  | Pham Dac Thinh | None | None
|  |  | Nguyen Thuy Nga | None | None
|  |  | Nguyen Duc Phuoc | None | None
|  |  | Le Thi Thuy Tram | None | None
|  |  | Le Xuan Luong | None | None
|  |  | Le Dang Thong | None | None
|  |  | Nguyen Bich Tram | None | None
|  |  | Duong Ngoc Danh | None | None
|  |  | Nguyen Duy Kiet | None | None
|  |  | Nguyen Quang Tu | None | None
|  |  | Ly Phuc Tho | None | None
|  |  | Pham Ngoc Hung | None | None
Summary of meeting content:
|  | Item | Deadline
|  | Team BA, update user story | 22:00 21/10/2024
|  | Team Dev continue code ui screen | 22:00 21/10/2024
Team Tester write testcase
Day 15 | Hoang Kim Tuan Anh
|  | Total number of attendees: | 15/26
|  | Absent member: | Pham Dac Thinh
Phan Dinh Yen
Nguyen Duc Phuoc
Nguyen Quang Hai
Ngo Tan Khoa
Le Dang Thong
Nguyen Bich Tram
Duong Ngoc Danh
Nguyen Duy Kiet
Nguyen Quang Tu
Pham Ngoc Hung
|  | Current progress of each member: | Name | Status | Notes
|  |  | Pham Dac Thinh | None | None
|  |  | Phan Dinh Yen | None | Have a schedule school
|  |  | Nguyen Duc Phuoc | None | Have a schedule school
|  |  | Nguyen Quang Hai | None | None
|  |  | Ngo Tan Khoa | None | None
|  |  | Le Dang Thong | None | None
|  |  | Nguyen Bich Tram | None | None
|  |  | Duong Ngoc Danh | None | None
|  |  | Nguyen Duy Kiet | None | None
|  |  | Nguyen Quang Tu | None | None
|  |  | Pham Ngoc Hung | None | None
Summary of meeting content:
|  | Item | Deadline
|  | Team BA: Write and edit the SRS document | 22:00 22/10/2024
|  | Team Dev: Continue coding and revise the code according to the comments from the recent code review. | 22:00 22/10/2024
|  | Team Tester: Continue writing test cases and learn how to use SQL for testing purposes | 22:00 22/10/2024
Day 16 | Tran Duy An
|  | Total number of attendees: | 13/26
|  | Absent member: | Pham Dac Thinh
Do Thi Quynh My
Nguyen Quang Hai
Le Dang Thong
Ngo Tan Khoa
Hoang Kim Tuan Anh
Nguyen Bich Tram
Duong Ngoc Danh
Nguyen Duy Kiet
Nguyen Quang Tu
Ly Phuc Tho
Pham Ngoc Hung
Van Phu Manh
|  | Current progress of each member: | Name | Status | Notes
|  |  | Pham Dac Thinh | None | None
|  |  | Do Thi Quynh My | None | Have a schedule school
|  |  | Nguyen Quang Hai | None | None
|  |  | Le Dang Thong | None | None
|  |  | Ngo Tan Khoa | None | None
|  |  | Hoang Kim Tuan Anh | None | None
|  |  | Nguyen Bich Tram | None | None
|  |  | Duong Ngoc Danh | None | None
|  |  | Nguyen Duy Kiet | None | None
|  |  | Nguyen Quang Tu | None | None
|  |  | Ly Phuc Tho | None | Have a schedule school
|  |  | Pham Ngoc Hung | None | None
|  |  | Van Phu Manh | None | Have a schedule school
Summary of meeting content:
|  | Item | Deadline
|  | Team BA: Write and edit SRS documents. | 22:00 23/10/2024
|  | Team Dev: Perform Unit test (API Testing) + Fixbug | 22:00 23/10/2024
|  | Team Tester: Learn how to test API + Write TC to test API. | 22:00 23/10/2024
Day 17 | Ly Phuc Tho
|  | Total number of attendees: | 16/26
|  | Absent member: | Phạm Đắc Thịnh
Nguyễn Thúy Nga
Lê Thị Thùy Trâm
Phan Đình Yên
Nguyễn Quang Hải
Lê Đặng Thông
Cao Nguyễn Vũ
Cai Hoàng Long
Ngô Tấn Khoa
Nguyễn Bích Trâm
Dương Ngọc Danh
Nguyễn Duy Kiệt
Nguyễn Quang Tú
Lý Phúc Thọ
PhamNgocHung
Nguyen Phan Ngoc Tran
|  | Current progress of each member: | Name | Status | Notes
|  |  | Pham Dac Thinh | None | None
|  |  | Nguyen Thuy Nga | None | Have a schedule school
|  |  | Le Thi Thuy Tram | None | Have a schedule school
|  |  | Phan Dinh Yen | None | Have a schedule school
|  |  | Nguyen Quang Hai | None | None
|  |  | Le Đang Thong | None | None
|  |  | Cao Nguyen Vu | None | Have a schedule school
|  |  | Cai Hoang Long | None | Have a schedule school
|  |  | Ngo Tan Khoa | None | None
|  |  | Nguyen Bich Tram | None | None
|  |  | Duong Ngoc Danh | None | None
|  |  | Nguyen Duy Kiet | None | None
|  |  | Nguyen Quang Tu | None | None
|  |  | Ly Phuc Tho | Late | None
|  |  | PhamNgocHung | None | None
|  |  | Nguyen Phan Ngoc Tran | None | None
Summary of meeting content:
|  | Item | Deadline
|  | Team BA: Write and edit SRS documents. | 22:00 24/10/2024
|  | Team Dev: Merge code + Fixbug | 22:00 24/10/2024
|  | Team Tester: Update TC + Write TC to test API. | 22:00 24/10/2024
Day 18 | Nguyen Le Quoc Bao
|  | Total number of attendees: | 17/26
|  | Absent member: | Nguyễn Thúy Nga
Lê Thị Thùy Trâm
Đỗ Thị Quỳnh My
Phan Đình Yên
Nguyen Duc Phuoc
HoangThiThanhTuyen
Cai Hoàng Long
Hoàng Kim Tuấn Anh
Trương Thị Bích Trâm
Nguyen Phan Ngoc Tran
Lê Văn Tuyến
NguyenLeQuocBao
Văn Phú Mạnh
|  | Current progress of each member: | Name | Status | Notes
|  |  | Phạm Đắc Thịnh | None | None
|  |  | Nguyễn Quang Hải | None | None
|  |  | Lê Xuân Lượng | None | None
|  |  | Lê Đặng Thông | None | None
|  |  | Cao Nguyễn Vũ | None | Have a schedule school
|  |  | Ngô Tấn Khoa | None | None
|  |  | Nguyễn Bích Trâm | None | None
|  |  | Dương Ngọc Danh | None | None
|  |  | Nguyễn Duy Kiệt | None | None
|  |  | Nguyễn Quang Tú | None | None
|  |  | Lý Phúc Thọ | None | Have a schedule school
|  |  | PhamNgocHung | None | None
Summary of meeting content:
|  | Item | Deadline
|  | Team BA: Write and edit SRS documents. | 22:00 25/10/2024
|  | Team Dev: Merge code + Fixbug | 22:00 25/10/2024
|  | Team Tester: Update TC + Write TC to test API. | 22:00 25/10/2024
Day 19 | Le Van Tuyen
Total number of attendees:
Absent member:
Current progress of each member:
Summary of meeting content:
|  | Item | Deadline
|  | BA: Submit SRS document | 16:00 28/10/2024
|  | Team DEV: Merge code + fix bug | 16:00 28/10/2024
Day 20 | Van Phu Manh
|  | Total number of attendees: | 16/26
|  | Absent member: | Name | Status | Notes
|  |  | Phạm Đắc Thịnh | None | None
|  |  | Phan Đình Yên | None | Have a schedule school
|  |  | Nguyễn Quang Hải | None | None
|  |  | Nguyen Duc Phuoc | None | Have a schedule school
|  |  | Lê Đặng Thông | None | None
|  |  | Nguyễn Bích Trâm | None | None
|  |  | Dương Ngọc Danh | None | None
|  |  | Nguyễn Duy Kiệt | None | None
|  |  | Nguyễn Quang Tú | None | None
|  |  | PhamNgocHung | None | None
|  | Summary of meeting content: | Item | Deadline
|  |  | make slides | 16:00 29/10/2024
|  |  | Team DEV: Merge code + fix bug | 16:00 29/10/2024
Day 21 | Truong Thi Bich Tram
|  | Total number of attendees: | 11/26
|  | Absent member: | Phạm Đắc Thịnh
Đỗ Thị Quỳnh My
Nguyễn Quang Hải
Lê Xuân Lượng
Hoàng Thị Thanh Tuyến
Lê Đặng Thông
Ngô Tấn Khoa
Hoàng Kim Tuấn Anh
Nguyễn Bích Trâm
Dương Ngọc Danh
Nguyễn Duy Kiệt
Nguyễn Quang Tú
Lý Phúc Thọ
Nguyen Phan Ngoc Tran
Văn Phú Mạnh
|  | Current progress of each member: | Name | Status | Notes
|  |  | Phạm Đắc Thịnh | None | None
|  |  | Đỗ Thị Quỳnh My | None | Have a schedule school
|  |  | Nguyễn Quang Hải | None | None
|  |  | Lê Xuân Lượng | None | None
|  |  | Hoàng Thị Thanh Tuyến | None | Have a schedule school
|  |  | Lê Đặng Thông | None | None
|  |  | Ngô Tấn Khoa | None | None
|  |  | Hoàng Kim Tuấn Anh | None | Have a schedule school
|  |  | Nguyễn Bích Trâm | None | None
|  |  | Dương Ngọc Danh | None | None
|  |  | Nguyễn Duy Kiệt | None | None
|  |  | Nguyễn Quang Tú | None | None
|  |  | Lý Phúc Thọ | None | None
|  |  | Nguyễn Phan Ngọc Trân | None | None
|  |  | Văn Phú Mạnh | None | Have a schedule school
Summary of meeting content:
|  | Item | Deadline
|  | BA: Demo the User story written and edited according to the change requirement. | 16:00 30/10/2024
|  | DEV: Demo the screens/functions coded | 16:00 30/10/2024
|  | TESTER: Demo the testcase and bugs you caught | 16:00 30/10/2024

## Trang tính2
Cột 1 | Cột 2 | Cột 3 | Cột 4 | Cột 5 | Cột 6