## Profile
Link Drive: https://drive.google.com/drive/folders/1ROngGvwjP2PN94MEDxBNcIlVzGIYWjOT | Link Github: https://github.com/thuctapnhom02/MockProject_102024_Nhom02.git | Link Google Meet: https://meet.google.com/xwz-fqbg-wwe?pli=1 | Q&A for mentor: https://docs.google.com/spreadsheets/d/1M6KmSUoYtG3F6JzmsL23puXaCT7DqHHG/edit | Link discord: https://discord.gg/jJ9NrrFe |  | Link Figma: https://www.figma.com/design/qUoKmTG6isRzuI8GfDjHQY/Qu%E1%BA%A3n-l%C3%BD-chung-c%C6%B0-t%E1%BA%A1i-Hoa-K%E1%BB%B3?node-id=0-1&node-type=canvas&t=jG1BK39V00CINQuH-0
Email của nhóm:
Danh sách thành viên:
STT | FULL NAME | LINK GITHUB | EMAIL | NUMBERPHONE | TEAM | NOTE | WORKBREAKDOWN | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-28 | 2024-10-29 | 2024-10-30
8 | Phạm Đắc Thịnh |  | thinhpd1805@gmail.com | 0777118502 | ReactJS | Out dự án | bar: 2024-10-08 to 2024-10-09; 2024-10-11; 2024-10-15 to 2024-10-30
10 | Nguyễn Thúy Nga |  | nnga16122003@gmail.com | 0934855740 | BA |  |  | 2024-10-17: Kẹt lịch trên trường; 2024-10-21: x; 2024-10-24: Kẹt lịch trên trường
11 | Lê Thị Thùy Trâm |  | lethithuytram140803@gmail.com | 0779440748 | BA |  |  | 2024-10-17: Kẹt lịch trên trường; 2024-10-21: x; 2024-10-24: Kẹt lịch trên trường
15 | Đỗ Thị Quỳnh My |  | mydo.17102003@gmail.com | 0344201912 | BA |  |  | 2024-10-09: x; 2024-10-22: Kẹt lịch trên trường; 2024-10-23: Kẹt lịch trên trường; 2024-10-30: Kẹt lịch trên trường
18 | Phan Đình Yên |  | dinhyenphan@gmail.com | 0364052889 | ReactJS |  |  | 2024-10-07: X; 2024-10-17: Kẹt lịch trên trường; 2024-10-24: Kẹt lịch trên trường; 2024-10-29: Kẹt lịch trên trường
| Nguyen Duc Phuoc |  | nguyenducphuoc0802@gmail.com | 965247483 | NodeJS | bar: 2024-10-22 to 2024-10-23; 2024-10-25; 2024-10-29 to 2024-10-30
21 | Nguyễn Quang Hải |  | nguyenhai250203@gmail.com | 968916540 | NodeJS | Out dự án |  | 2024-10-21: x; 2024-10-22: Kẹt lịch trên; 2024-10-28: x; 2024-10-29: Kẹt lịch trên trường
33 | Lê Xuân Lượng |  | lexuanluongllhh@gmail.com | 961195409 | ReactJS | bar: 2024-10-03 to 2024-10-04; 2024-10-18 to 2024-10-21; 2024-10-25; 2024-10-30
34 | HoangThiThanhTuyen |  | hoangthithanhtuyen2003@gmail.com | 905941143 | Tester |  |  | 2024-10-09: x; 2024-10-30: Kẹt lịch trên trường
44 | Lê Đặng Thông |  | ldthong2003@gmail.com | 792530225 | Python Fullstack | Out dự án | bar: 2024-10-07 to 2024-10-08; 2024-10-11; 2024-10-15 to 2024-10-23; 2024-10-25 to 2024-10-30
46 | Cao Nguyễn Vũ |  | caonguyenvu191@gmail.com | 335268591 | Java Back-End |  |  | 2024-10-03: x; 2024-10-04: x; 2024-10-17: Kẹt lịch trên trường; 2024-10-25: Kẹt lịch trên trường
47 | Cai Hoàng Long |  | 21115053120123ute@gmail.com | 076 419 7093 | Java Back-End |  |  | 2024-10-17: Kẹt lịch trên trường
54 | Ngô Tấn Khoa |  | nkhoa6869@gmail.com | 935552021 | Tester | Out dự án | bar: 2024-10-03 to 2024-10-07; 2024-10-18; 2024-10-22 to 2024-10-23; 2024-10-25; 2024-10-30
56 | Hoàng Kim Tuấn Anh | https://github.com/Tuananh458 | tuananhhk458@gmail.com | 328778334 | Java Back-End |  |  | 2024-10-16: x; 2024-10-23: x; 2024-10-30: Kẹt lịch trên trường
58 | Nguyễn Bích Trâm |  | tram01122021@gmail.com | 386488232 | Tester | out dự án | bar: 2024-10-02 to 2024-10-30
62 | Dương Ngọc Danh |  | duongngocdanh6@gmail.com | 94610344 | Java Back-End | out dự án | bar: 2024-10-02 to 2024-10-30
63 | Nguyễn Duy Kiệt |  | nguyenduykiet72@gmail.com | 333249520 | Java Back-End | out dự án | bar: 2024-10-02 to 2024-10-30
72 | Nguyễn Quang Tú |  | nguyenquangtu190203@gmail.com | 327231963 | Kiến tập | Out dự án | bar: 2024-10-02 to 2024-10-11; 2024-10-15 to 2024-10-30
74 | Lý Phúc Thọ |  | tholy2004@gmail.com | 357376158 | Java Back-End |  |  | 2024-10-16: x; 2024-10-17: x; 2024-10-21: x; 2024-10-23: Kẹt lịch trên trường; 2024-10-25: Kẹt lịch trên trường; 2024-10-30: x
87 | Trần Duy An |  | ann087571@gmail.com | 335836843 | ReactJS
102 | PhamNgocHung |  | phngochung3001@gmail.com | 779079471 | Java Back-End | out dự án | bar: 2024-10-02 to 2024-10-29
103 | Nguyen Phan Ngoc Tran |  | ntran18904@gmail.com | 388255210 | ReactJS | bar: 2024-10-03 to 2024-10-04; 2024-10-11; 2024-10-30
106 | Lê Văn Tuyến | https://github.com/Miku2906 | tuyenle2906@gmail.com | 326415148 | Python Fullstack | bar: 2024-10-14
107 | NguyenLeQuocBao | https://github.com/ambrouse | ngbao3558@gmail.com | 948093484 | Java Back-End | bar: 2024-10-07; 2024-10-14
126 | Văn Phú Mạnh |  | vanphumanh14042003@gmail.com | 706079191 | Java Back-End |  |  | 2024-10-23: Kẹt lịch trên trường; 2024-10-30: Kẹt lịch trên trường
127 | Trương Thị Bích Trâm |  | tramtruong160203@gmail.com | 865983219 | Java Back-End

## Group List
Team 1
Trần Duy An |  | ReactJS | Staff -(Home - Assignment - Work Contract - Edit Profile ) + Header-Footer
Hoàng Kim Tuấn Anh |  | Java Back-End
Lý Phúc Thọ |  | Java Back-End
Team 2
Phan Đình Yên |  | ReactJS | Admin (Home-Account-Financial-Personal management)
Cao Nguyễn Vũ |  | Java Back-End
Cai Hoàng Long |  | Java Back-End
Team 3
Phạm Đắc Thịnh | Out dự án! | ReactJS | User - (Resident): User Home - Rental request form - Schedule a home inspection - Personal Information,Contracts - Rental request form, Maintenance and Repair Requests, Submit a maintenance/ repair request. Payment, Payment with banking. Notifications.
Nguyễn Quang Hải |  | NodeJS
Nguyen Duc Phuoc |  | NodeJS
Team 4
Lê Xuân Lượng |  | ReactJS | Home Page, Apartment list, Apartment details, Sign Up,Sign In
Lê Đặng Thông | Out dự án! | Python Fullstack
Team 5
Lê Văn Tuyến |  | Python Fullstack | Admin (Asset… -Resident management and payment-Personal management)
NguyenLeQuocBao |  | Java Back-End
Team 6
Nguyen Phan Ngoc Tran |  | ReactJS | Admin(Contract Management, Complaint management, repair requests management)
Văn Phú Mạnh |  | Java Back-End
Trương Thị Bích Trâm |  | Java Back-End

## Assignment
| Task | Detail | Role | Team | Job Details | Status | Start Date | End Date | Complete
1 | SC_066 | Complaint handling staff- List complaints. | staff | 1 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
2 | SC_067 | Complaint handling staff-Complaint detail. | staff | 1 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
3 | SC_068 | Technical staff- System maintenance list | staff | 1 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
4 | SC_069 | Technical staff- Details of system condition. | staff | 1 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
5 | SC_070 | Technical staff- List repair requirements | staff | 1 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
6 | SC_071 | Technical staff- Repair request detail. | staff | 1 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
7 | Header-Footer | Layout background | Admin, User, Staff | 1 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
8 | SC_022 | Home | Admin | 2 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
9 | SC_023, SC_024, SC_025 | Account management | Admin | 2 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
10 | SC_026, SC_029, SC_030, SC_027, SC_028 | Financial management - Income | Admin | 2 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
11 | SC_031, SC_032 | Financial management_Outcome | Admin | 2 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
12 | SC_006, SC_007, SC_008 | Schedule a home inspector, Rental request form. Personal Information, Contracts. | User | 3 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
13 | SC_009, SC_010 | Maintenance and repair request, Submit a maintenance/ repair request | User | 3 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
14 | SC_011, SC_012, SC_013, SC_014 | Payment | User | 3 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
15 | SC_015, SC_016 | Payment method | User | 3 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
16 | SC_017, SC_018 | Notification | User | 3 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
17 | SC_019, SC_020, SC_021 | Complaints | User | 3 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
18 | SC_001, SC_002, SC_003 | Login-SignUp Interface, Home_Page(Landing) | Admin, User, Staff | 4 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
19 | SC_004, SC_005, | Apartment List, Apartment Detail | Admin, User, Staff | 4 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
20
21 | SC_62 | Admin-List of complaints. | admin | 5 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
22 | SC_63 | Admin-Complaint detail. | admin | 5 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
23 | SC_64 | Admin- List of repair requirements. | admin | 5 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
24 | SC_65 | Admin-Repair request details. | admin | 5 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
25 | SC_033 | Resident management and payment | Admin | 5 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
26 | SC_034, SC_035 | Personal management | Admin | 5 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
27 | SC_036, SC_037, SC_038, SC_039 | Admin system management. | Admin | 5 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
28 | SC_40 | General contract statistics | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
29 | SC_41 | Lease contract management | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
30 | SC_42 | Add a new lease contract. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
31 | SC_43 | Lease contract details. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
32 | SC_44 | Payment history of a lease contract | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
33 | SC_45 | Breach of a lease contract. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
34 | SC_46 | Service contract management: | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
35 | SC_47 | Add a new service contract: | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
36 | SC_48 | Service contract details. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
37 | SC_49 | Payment history of a service contract. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
38 | SC_50 | Utility contract management. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
39 | SC_51 | Add a new utility contract: | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
40 | SC_52 | Utility contract details. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
41 | SC_53 | Payment history of a utility contract. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
42 | SC_54 | Supplier contract. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
43 | SC_55 | Add a new supplier contract. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
44 | SC_56 | Supplier contract details. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
45 | SC_57 | Payment of a supplier contract. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
46 | SC_59 | Employee contract management. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
47 | SC_60 | Add a new employee contract. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
48 | SC_61 | Employee contract details. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE
49 | SC_58 | Equipment maintenance history. | admin | 6 | Design Interface And Connect Database | In process | 2024-10-14 | 2024-10-25 | FALSE

## TASK FIGMA
ROLE: |  |  | COMPLETE
| ADMIN | Home | TRUE
| ADMIN | Account Management | TRUE
| ADMIN | Account information | TRUE
| ADMIN | Add new account | FALSE
| ADMIN | Financial management_Income | TRUE
| ADMIN | Add new income | TRUE
| ADMIN | Send Notification | FALSE
| ADMIN | Financial management_Outcome | TRUE
| ADMIN | Add new costs | TRUE
| ADMIN | Resident management and payments | TRUE
| ADMIN | Admin-List of staff | TRUE
| ADMIN | Add staff | TRUE
| ADMIN | Information building | TRUE
| ADMIN | add system needs maintenance | TRUE
| ADMIN | Details of system condition | TRUE
| ADMIN | General contract statistics | FALSE
| ADMIN | Lease contract management | TRUE
| ADMIN | Add a new lease contract | TRUE
| ADMIN | Lease contract details | TRUE
| ADMIN | Payment history of a lease contract | FALSE
| ADMIN | Breach of a lease contract | FALSE
| ADMIN | Service contract management | FALSE
| ADMIN | Add a new service contract | FALSE
| ADMIN | Service contract details | FALSE
| ADMIN | Payment history of a service contract | FALSE
| ADMIN | Utility contract management | FALSE
| ADMIN | Add a new utility contract | FALSE
| ADMIN | Utility contract details | FALSE
| ADMIN | Payment history of a utility contract | FALSE
| ADMIN | Supplier contract | FALSE
| ADMIN | Add a new supplier contract | FALSE
| ADMIN | Admin-Repair request details. | TRUE
| ADMIN | Admin- List of repair requirements. | TRUE
| ADMIN | Admin-Complaint detail. | FALSE
| ADMIN | Admin-List of complaints. | TRUE
| ADMIN | Employee contract details. | FALSE
| ADMIN | Employee contract details. | FALSE
| ADMIN | Employee contract management. | FALSE
| ADMIN | Equipment maintenance history. | FALSE
| ADMIN | Payment of a supplier contract. | FALSE
| ADMIN | Supplier contract details | FALSE
| ADMIN | Add a new supplier contract | FALSE
ROLE: | USER | User-Login | TRUE
| USER | User-Signup. | FALSE
| USER | User-Home. | FALSE
| USER | User-Apartment List. | FALSE
| USER | User- Apartment Detail. | FALSE
| USER | User-Schedule a home inspector. | FALSE
| USER | User-Rental request form. | FALSE
| USER | User – Personal Information, Contracts. | FALSE
| USER | User – Maintenance and repair request. | FALSE
| USER | User – Submit a maintenance/ repair request. | FALSE
| USER | User – Payment - list | FALSE
| USER | User – Payment - detail | FALSE
| USER | User – Payment - unpaid | FALSE
| USER | User – Payment - method | FALSE
| USER | Payment with banking. | FALSE
| USER | Payment with credit card. | FALSE
| USER | My notifications. | FALSE
| USER | Notification detail. | FALSE
| USER | My complaints. | FALSE
| USER | Submit a complaint. | FALSE
| USER | History of my complaints. | FALSE
ROLE: | STAFF | Technical staff- Repair request detail. | TRUE
| STAFF | Technical staff- List repair requirements. | TRUE
| STAFF | Technical staff- Details of system condition. | FALSE
| STAFF | Technical staff- System maintenance list. | FALSE
| STAFF | Complaint handling staff-Complaint detail. | FALSE
| STAFF | Complaint handling staff- List complaints. | FALSE